Deployment Package

Project Management

Basic Profile

Notes: This document is the intellectual propriety of its author’s organization. However, information contained in this document is free of use. The distribution of all or parts of this document is authorized for non commercial use as long as the following legal notice is mentioned: © Rory O’Connor, Lero and Dublin City University Commercial use of this document is strictly forbidden. This document is distributed in order to enhance exchange of technical and scientific information. This material is furnished on an “as-is” basis. The author(s) make(s) no warranties of any kind, either expressed or implied, as to any matter including, but not limited to, warranty of fitness for purpose or merchantability, exclusivity, or results obtained from use of the material. The processes described in this Deployment Package are not intended to preclude or discourage the use of additional processes that Very Small Entities may find useful. This document is available free of charge at: http://profs.logti.etsmtl.ca/claporte/English/VSE/index.html http://www.lero.ie/research/internationalprojects/softwareprocessesforsmallenterprises/

| Author | R. O’Connor - Irish Software Engineering Research Centre (Ireland) |
| --- | --- |
| Editors | C. Y. LAPORTE – École de Technologie Supérieure (ETS), (Canada) ANA VAZQUEZ – 5th level, (México) |
| Creation date | 04/08/2007 |
| Last update | 13 August 2009 |
| Status | Draft |
| Version | 1.3 |

Version History

| Date | Version | Author | Modification |
| --- | --- | --- | --- |
| 04/04/2008 | 0.1 | R. O’Connor | Document Creation |
| 08/04/2008 | 0.2 | R. O’Connor | Self review |
| 10/04/2008 | 1 | R. O’Connor | First draft version sent to ETS / CETIC |
| 12/05/2008 | 1.2 | C. Laporte | Comments & corrections |
| 13/08/2009 | 1.3 | R. O’Connor | Substantially revised and updated. Note this version based on: - Template version 03CL - Part 5 version 724HYD-026 29110-5-1 TR VSE Management and Engineering Guide for Basic Profile PDTR3 25JB.doc |

Abbreviations/Acronyms

| Abre./Acro. | Definitions |
| --- | --- |
| DP | Deployment Package - a set of artefacts developed to facilitate the implementation of a set of practices, of the selected framework, in a Very Small Entity. |
| VSE | Very Small Entity – an enterprise, organization, department or project having up to 25 people. |
| VSEs | Very Small Entities |

Table of Contents

1. Technical Description	4

Purpose of this document	4

Why Process Project Management is Important?	4

2. Definitions	6

Generic Terms	6

Specific Terms	6

3. Relationships with ISO/IEC 29110	7

4. Description of Processes, Activities, Tasks, Steps, Roles & Products	9

Project Planning Process	10

Project Plan Execution	12

Project Assessment and Control Process	13

Project Closure	15

Role Description	16

Product Description	16

Artefact Description	20

5. Template	21

6. Example	24

Example of Project Management Practices Lifecycle	24

7. Checklist	25

Project Plan Review Checklist	25

8. Tool	26

9. Reference to Other Standards and Models	27

ISO 9001 Reference Matrix	27

ISO/IEC 12207 Reference Matrix	27

CMMI Reference Matrix	27

10. References	28

11. Evaluation Form	29

# 1. Technical Description

## Purpose of this document

This Deployment Package (DP) supports the Basic Profile as defined in ISO/IEC 29110 Part 5-1-2: Management and Engineering Guide. A DP is a set of artefacts developed to facilitate the implementation of a set of practices in a Very Small Entity (VSE). A DP is not a process reference model (i.e. it is not prescriptive). The elements of a typical DP are: description of processes, activities, tasks, roles and products, template, checklist, example, and reference to standards and models, and tools.

This document supports Profile 1 as defined in ISO/IEC 29110, and consists of the following parts, under the general title Software Engineering — Lifecycle Profiles for Very Small Entities (VSE) Part 5-1-2: Management and Engineering Guide.

The content of this document is entirely informative.

This document has been produced by Lero (The Irish Software Engineering Research Centre – www.lero.ie) and DCU (Dublin City University – www.computing.dcu.ie) beyond their official participation to ISO JTC1/SC7/WG24.

## Why Process Project Management is Important?

Many software products fail not because there is no market, but because the cost of creating the software far outstrips any profit. Currently approximately half a million project managers worldwide are responsible for one million software projects each year, which produce software worth USD$600 billion. It is now accepted that many of these projects fail to fulfil customers' expectations or fail to deliver the software within budget and on schedule [Jalote02]. Putnam suggests that about one-third of projects have cost and schedule overruns of more than 125% [Putnam97].

Project Management Failure

Software project failure is often devastating to an organization. Schedule slips, buggy releases and missing features can mean the end of the project or even financial ruin for a company. Some of the major reasons for projects running out of control are: unclear objectives; bad planning; new technology; a lack of a project management methodology; and insufficient staff [Jalote02]. At least three of these five reasons clearly relate to project management. The other two - insufficient staff and new technology - can be considered as risks whose management is also a part of project management.

While there are many reasons why software projects fail, one of the most important is incorrect management of the project. Good project management cannot guarantee project success, however bad project management usually results in project failure. The software is delivered late, costs more and fails to meet its requirements. [Sommerville06]. Clearly, by using effective project management techniques a project manager can improve the chances of success.

A study by Capers Jones [Jones04] of approximately 250 software projects between 1995 and 2004 shows an interesting pattern. When comparing projects that successfully achieved their cost and schedule estimates against those that ran late, were over budget, or were cancelled without completion, six common problems were observed: poor project planning, poor cost estimating, poor measurements, poor milestone tracking, poor change control, and poor quality control. By contrast, successful software projects tended to be better than average in all six of these areas. Perhaps the most interesting aspect of these six problem areas is that all are associated with project management rather than with technical personnel.

Project Management Success

There are many ways to make large software systems fail. There are only a few ways of making them succeed. It is commonly agreed that project management is the key factor that tends to push projects along either the path to success or the path to failure. Among the most important project management practices leading to success are those of planning and estimating before the project starts, absorbing changing requirements during the project, and successfully minimizing bugs or defects.

Successful projects always excel in these critical activities: planning, estimating, change control, and quality control. By contrast, projects that run late or fail typically had flawed or optimistic plans, had estimates that did not anticipate changes or handle change well, and failed to control quality [Jones04].

# 2. Definitions

In this section, the reader will find two sets of definitions. The first set defines the terms used in all Deployment Packages, i.e. generic terms. The second set of terms used in this Deployment package, i.e. specific terms.

## Generic Terms

Process: set of interrelated or interacting activities which transform inputs into outputs [ISO/IEC 12207].

Activity: a set of cohesive tasks of a process [ISO/IEC 12207].

Task: required, recommended, or permissible action, intended to contribute to the achievement of one or more outcomes of a process [ISO/IEC 12207].

Sub-Task: When a task is complex, it is divided into sub-tasks.

Step: In a deployment package, a task is decomposed in a sequence of steps.

Role: a defined function to be performed by a project team member, such as testing, filing, inspecting, coding. [ISO/IEC 24765]

Product: piece of information or deliverable that can be produced (not mandatory) by one or several tasks. (e. g. design document, source code).

Artefact: information, which is not listed in ISO/IEC 29110 Part 5, but can help a VSE during the execution of a project.

## Specific Terms

Resource: an asset that is utilized or consumed during the execution of a process [ISO/IEC 12207]

Project: an endeavour with defined start and finish dates undertaken to create a product or service in accordance with specified resources and requirements [ISO/IEC 12207]

WBS: A Work Breakdown Structure (WBS): is a fundamental project management technique for defining and organizing the total scope of a project, using a hierarchical tree structure. The first two levels of the WBS (the root node and Level 2) define a set of planned outcomes that collectively and exclusively represent 100% of the project scope. At each subsequent level, the children of a parent node collectively and exclusively represent 100% of the scope of their parent node. [Dalcher07].

# 3. Relationships with ISO/IEC 29110

This deployment package covers the activities related to Project Management of the ISO Technical Report ISO/IEC 29110 Part 5-1-2 for Very Small Entities (VSEs) – Basic Profile [ISO/IEC29110].

In this section, the reader will find a list of Project Management (PM) and Software Implementation (SI) process, activities, tasks and roles from Part 5 that are directly related to this topic. This topic is described in details in the next section.

- Process: 4.2 Project Management Process (PM)

- Activity: PM1 Project Planning

- Tasks and Roles:

| Tasks | Roles |
| --- | --- |
| PM.1.1 Review the Statement of Work | PM, TL |
| PM.1.2 Define with the Customer the Delivery Instructions of each one of the deliverables specified in the Statement of Work. | PM, CUS |
| PM.1.3 Identify the specific tasks to be performed in order to produce the deliverables and their software components identified in the Statement of Work. | PM, TL |
| PM.1.4 Establish the Estimated Duration to perform each task. | PM, TL |
| PM.1.5 Identify and document the resources: human, material, equipment and tools, including the required training of the Work Team to perform the project. | PM, TL |
| PM.1.6 Establish the Composition of Work Team assigning roles and responsibilities according to the Resources. | PM, TL |
| PM.1.7 Assign estimated start and completion dates to each one of the tasks in order to create the Schedule of the Project Tasks taking into account the assigned resources, sequence and dependency of the tasks. | PM, TL |
| PM.1.8 Calculate and document the project Estimated Effort and Cost. | PM |
| PM.1.9 Identify and document the risks which may affect the project. | PM, TL |
| PM.1.10 Document the Version Control Strategy in the Project Plan. | PM, TL |
| PM.1.11 Generate the Project Plan or update it. Furthermore, the Project Plan can be updated due to the Change Request made by the Customer or arising from the project. | PM |
| PM.1.12 Include product description, scope, objectives and deliverables in the Project Plan. | PM, TL |
| PM.1.13 Verification of the Project Plan. Verify that all Project Plan elements are viable and consistent. | PM, TL |
| PM.1.14 Validation of the Project Plan. Validate that the Project Plan elements definition match with the Statement of Work. | PM, CUS |
| PM.1.15 Establish or prepare the project repository using the Version Control Strategy. | PM, TL |

- Process: 4.2 Project Management Process

- Activity: PM.2 Project Plan Execution

- Tasks and Roles:

| Task | Roles |
| --- | --- |
| PM.2.1 Review the Project Plan and record actual data in Progress Status Record. | PM, TL, WT |
| PM.2.2 Analyze and evaluate the Change Request for cost, schedule and technical impact, and include the accepted changes in the Project Plan. | PM, TL |
| PM.2.3 Conduct revision meetings with the Work Team, review risk status, record agreements and track them to closure. | PM, TL |
| PM.2.4 Conduct revision meetings with the Customer, record agreements and track them to closure. | PM, CUS, TL, WT |
| PM.2.5 Perform backup according to the Version Control Strategy. | PM |
| PM.2.6 Perform Project Repository recovery using the Project Repository Backup, if necessary. | PM |

- Process: 4.2 Project Management Process

- Activity: PM.3 Project assessment and control

- Tasks and Roles:

| Task | Roles |
| --- | --- |
| PM.3.1 Evaluate project progress with respect to the Project Plan | PM, TL, WT |
| PM.3.2 Establish actions to correct deviations or problems and identified risks concerning the accomplishment of the plan, as needed, document them in Correction Register and track them to closure. | PM, TL, WT |
| PM.3.3 Identify changes to requirements and/or Project Plan to address major deviations, potential risks or problems concerning the accomplishment of the plan, document them in Change Request and track them to closure. | PM, TL, WT |

- Process: 4.2 Project Management Process

- Activity: PM.4 Project closure

- Tasks and Roles:

| Task | Roles |
| --- | --- |
| PM.4.1. Formalize the completion of the project according to the Delivery Instructions established in the Project Plan, providing acceptance support and getting the Acceptance Record signed. | PM, CUS |
| PM.4.2 Update Project Repository. | PM |

# 4. Description of Processes, Activities, Tasks, Steps, Roles & Products

Figure 1 Overview of Project Management Practices

Process: 4.2 Project Management Process (PM)

Activity: PM1 Project Planning

| Tasks | Roles |
| --- | --- |
| PM.1.1 Review the Statement of Work | PM, TL |
| PM.1.2 Define with the Customer the Delivery Instructions of each one of the deliverables specified in the Statement of Work. | PM, CUS |
| PM.1.3 Identify the specific tasks to be performed in order to produce the deliverables and their software components identified in the Statement of Work. | PM, TL |
| PM.1.4 Establish the Estimated Duration to perform each task. | PM, TL |
| PM.1.5 Identify and document the resources: human, material, equipment and tools, including the required training of the Work Team to perform the project. | PM, TL |
| PM.1.6 Establish the Composition of Work Team assigning roles and responsibilities according to the Resources. | PM, TL |
| PM.1.7 Assign estimated start and completion dates to each one of the tasks in order to create the Schedule of the Project Tasks taking into account the assigned resources, sequence and dependency of the tasks. | PM, TL |
| PM.1.8 Calculate and document the project Estimated Effort and Cost. | PM |
| PM.1.9 Identify and document the risks which may affect the project. | PM, TL |
| PM.1.10 Document the Version Control Strategy in the Project Plan. | PM, TL |
| PM.1.11 Generate the Project Plan or update it. Furthermore, the Project Plan can be updated due to the Change Request made by the Customer or arising from the project. | PM |
| PM.1.12 Include product description, scope, objectives and deliverables in the Project Plan. | PM, TL |
| PM.1.13 Verification of the Project Plan. Verify that all Project Plan elements are viable and consistent. | PM, TL |
| PM.1.14 Validation of the Project Plan. Validate that the Project Plan elements definition match with the Statement of Work. | PM, CUS |
| PM.1.15 Establish or prepare the project repository using the Version Control Strategy. | PM, TL |

## Project Planning Process

| Objectives: | The primary objective of the Project Planning Process is to produce and communicate effective and workable project plans. This process determines the scope of the project management and technical activities, identifies process outputs, project tasks and deliverables, establishes schedules for project task conduct, including achievement criteria, and required resources to accomplish project tasks. |
| --- | --- |
| Rationale: | Whatever the size of the project, good planning is essential if it is to succeed. Effective software project management depends on thoroughly planning the progress of a project. A plan formulated at the start of a project should act as a driver for the project. The initial plan should be the best possible plan given the available information. It should evolve as the project progresses and better information becomes available. |
| Roles: | Project Manager |
|  | Analyst |
|  | Customer |
| Artefacts: | Project Plan |
|  | Project Description |
| Steps: | 1. Identify products and activities |
|  | 2. Create a WBS (work breakdown structure) |
|  | 3. Estimate resources, effort and duration |
|  | 4. Create a schedule |
| Step Description: | Step 1. Identify products and activities: During this stage the project manager identifies all the products, tasks and activities that need to be completed before the project can be finished. It may be necessary for the project manager to liaise with the customer and the analyst to fully understand the objectives of the project and to break down each one into its constituent parts. Step 2. Create a WBS (Work Breakdown Structure): The WBS aims to identify all of the projects tasks that need to be completed and organises them in a hierarchal format, where smaller sub-tasks contribute to the completion of a larger task at a higher level. A typical WBS would consist of: - Project - Task - Sub-Task - Work Package - Effort Once a WBS is complete, project milestones (key deliverables) can be identified and may be used for project tracking. Tips: Many software packages such as MS Project can structure WBS information and automatically generate useful graphical representations. Step 3. Estimate resources, effort and duration: For each task in the WBS the effort and duration should be estimated and the overall resources required to complete the project calculated. Typically a ‘bottom-up’ approach is used to estimate the effort requires for each task in the WBS in terms of person hours or person days. In order to create a schedule of tasks and estimate total project budget, it is necessary to estimate the resources (people, equipment, services, etc.) required to complete each task. Step 4. Create a schedule: Tasks should be organised into a coherent sequence, including parallel activities, and mapped against time and resources, to produce a schedule of tasks to be completed by individuals during the lifetime of the project. Communications: Confirm all previous steps are fully communicated to all parties by: - Distributing all output reports to all parties, in particular those that must do the tasks, or be influenced by the outcome of the tasks or schedules. - Holding a meeting(s) with all participants to ensure any queries are raised and actioned, or assigned for action. Tips: - When scheduling task execution ensure the percentage of time each participant has to allocate to the project is taken into account, thus if the task should take 3 days full time and the task owner can only allocate one day a week then the task duration will take 15 days elapsed time. - Many software packages such as MS Project can assist with capturing data about tasks in a WBS and generating Activity Network diagrams and Gantt charts. |

Process: 4.2 Project Management Process (PM)

Activity: PM.2 Project Plan Execution

| Task | Roles |
| --- | --- |
| PM.2.1 Review the Project Plan and record actual data in Progress Status Record. | PM, TL, WT |
| PM.2.2 Analyze and evaluate the Change Request for cost, schedule and technical impact, and include the accepted changes in the Project Plan. | PM, TL |
| PM.2.3 Conduct revision meetings with the Work Team, review risk status, record agreements and track them to closure. | PM, TL |
| PM.2.4 Conduct revision meetings with the Customer, record agreements and track them to closure. | PM, CUS, TL, WT |
| PM.2.5 Perform backup according to the Version Control Strategy. | PM |
| PM.2.6 Perform Project Repository recovery using the Project Repository Backup, if necessary. | PM |

## Project Plan Execution

| Objectives: | To implement the actual work tasks of the project in accordance with the project plan. |
| --- | --- |
| Rationale: | Ideally when the project plan has been agreed and communicated to all teams members, work of the development of the product which is the subject of the project should commence. |
| Roles: | Project Manager |
|  | Analyst |
|  | Developer |
|  | Customer |
| Artefacts: | Project Plan |
|  | Project Status Record |
|  | Change Requests |
| Steps: | 1. Obtain agreement on project plan |
|  | 2. Record status |
|  | 3. Take corrective action |
| Step Description: | Step 1. Agreement on project plan: Agreement must be reached between all the project managers and all members of the project team on the defined project parameters and targets as set out in the project plan. It may also be necessary to gain the agreement of the customer in terms of project duration and deliverables schedule. Step 2. Record status: The project manager should monitor and record the actual progress of the project against the planned progress. A record of the actual project data should be maintained in a Progress Status Record. To record status a ‘traffic light system’ could be used. The Red / Yellow / Green traffic light approach is one used commonly in project management as it is a colour theme everyone is familiar with. The colour are: - Green – task is ‘on target’ - Yellow – task is ‘not on target but recoverable’ - Red – task is ‘not on target and recoverable only with difficulty’ The typical contents of such a record are: - status of actual tasks against planned tasks - status of actual results against established objectives / goals - status of actual resource allocation against planned resources - status of actual cost against budget estimates - status of actual time against planned schedule - status of actual risk against previously identified Step 3. Corrective action: When deviations between the project plan and actual project progress have been indentified or the implementation of change requests agreed, corrective action will need to be taken to ensure than project continues according to revised plan. |

Process: 4.2 Project Management Process (PM)

- Activity: PM.3 Project assessment and control

| Task | Roles |
| --- | --- |
| PM.3.1 Evaluate project progress with respect to the Project Plan | PM, TL, WT |
| PM.3.2 Establish actions to correct deviations or problems and identified risks concerning the accomplishment of the plan, as needed, document them in Correction Register and track them to closure. | PM, TL, WT |
| PM.3.3 Identify changes to requirements and/or Project Plan to address major deviations, potential risks or problems concerning the accomplishment of the plan, document them in Change Request and track them to closure. | PM, TL, WT |

## Project Assessment and Control Process

| Objectives: | The purpose of the Project Assessment and Control is to determine the status of the project and ensure that the project performs according to plans and schedules, within projected budgets and it satisfies technical objectives. This process includes redirecting the project activities, as appropriate, to correct identified deviations and variations from other project management or technical processes. Redirection may include re-planning as appropriate. |
| --- | --- |
| Rationale: | A project plan is a document that can be used to guide the execution of a project. Unless the actual performance of the execution of the project is tracked against the plan, the plan will have limited value beyond the initiation of the project. |
| Roles: | Project Manager |
|  | Developer |
| Artefacts: | Project Plan |
|  | Project Status Record |
|  | Change Requests |
| Steps: | 1. Review plan |
|  | 2. Identify plan deviations |
|  | 3. Process change requests |
| Step Description: | Step 1. Review plan: Periodically the project plan should be reviewed by the project manager against the actual progress as recorded in the Progress Status Record. Deviation from planned progress may require Corrective Action to be performed, resulting in an updated project plan. Attention should be paid to identifying and documenting any risks which may affect the project. Step 2. Identify plan deviations: Based on any deviations discovered during the Review Plan activity, it may be necessary to identify and evaluate significant cost, schedule and technical performance deviations and undertake Corrective Actions. Step 3. Process change requests: Requirements change requests (any change that comes in after project has started) must be managed and controlled, as there will be an impact on the project plan, schedule and cost. Typically for a change request the following steps should be undertaken: - Perform an impact analysis of the change on the work product - Estimate effort to implement change - Re-estimate project schedule and cost - Obtain customer sign-off on agree change |

Process: 4.2 Project Management Process (PM)

Activity: PM.4 Project closure

| Task | Roles |
| --- | --- |
| PM.4.1. Formalize the completion of the project according to the Delivery Instructions established in the Project Plan, providing acceptance support and getting the Acceptance Record signed. | PM, CUS |
| PM.4.2 Update Project Repository. | PM |

## Project Closure

| Task Name |  |
| --- | --- |
| Objectives: | Project Closure typically involves releasing the final deliverables to the customer, handing over project documentation to the business, terminating supplier contracts, releasing project resources and communicating project closure to all stakeholders. Often a final step is to undertake a Post Implementation Review (post-mortem) to identify the level of project success and note any lessons learned for future projects. |
| Rationale: | A project closure process ensures that all project outputs are delivered, recorded and lessons learned from a post-delivery review. |
| Roles: | Project Manager |
|  | Customer |
| Artefacts: | Project plan |
|  | Software |
|  | Acceptance document |
| Steps: | 1. Deliver software |
|  | 2. Obtain customer acceptance |
|  | 3. Baseline product documentation |
|  | 4. Conduct project closure analysis |
| Step Description: | Step 1. Deliver software: The software system and associated documentation is delivered to the customer. Step 2. Customer acceptance: The signing of an Acceptance Document by the customer indicates the formal the closure of the project and that the software has been delivered as specified in the contract delivery instructions. Step 3. Baseline product documentation: As there may be multiple versions of the product over time and/or continued product maintenance, it is necessary to formally record all major project documentation (such as requirements, project plans, software product, acceptance, etc.) at closure stage. Step 4. Project closure analysis: A post-delivery review (project post-mortem or project retrospective) is conducted and the outcome analysed to understand possible lessons which may be learned and knowledge gained for future projects. Understanding why a project was successful or failed is a key part of the learning process, which leads to improvement in the software development process. |

## Role Description

This is an alphabetical list of the roles, abbreviations and list of competencies as defined in Part 5.

|  | Role | Abbreviation | Competency |
| --- | --- | --- | --- |
| 1. | Customer | CUS | Knowledge of the Customer processes and ability to explain the Customer requirements. The Customer (representative) must have the authority to approve the requirements and their changes. The Customer includes user representatives in order to ensure that the operational environment is addressed. Knowledge and experience in the application domain. |
| 2. | Project Manager | PM | Leadership capability with experience making decisions, planning, personnel management, delegation and supervision, finances and software development. |
| 3. | Technical Leader | TL | Knowledge and experience in the software process domain. |
| 4 | Work Team | WT | Knowledge and experience according to their roles on the project: AN, DES, and/or PR. Knowledge on the standards used by the Customer and/or by the VSE. |

## Product Description

This is an alphabetical list of the input, output and internal process products, its descriptions, possible states and the source of the product.

|  | Name | Description | Source |
| --- | --- | --- | --- |
| 1. | Acceptance Record | Documents the customer acceptance of the Deliverables of the project. It may have the following characteristics: - Record of the receipt of the delivery - Identifies the date received - Identifies the delivered elements - Records the verification of any Customer acceptance criteria defined - Identifies any open issues (if applicable) - Signed by receiving Customer | Project Management |
| 2. | Change Request | Identifies a Software, or documentation problem or desired improvement, and requests modifications. It may have the following characteristics: - Record of the receipt of the delivery - Identifies purpose of change - Identifies request status - Identifies requester contact information - Impacted system(s) - Impact to operations of existing system(s) defined - Impact to associated documentation defined - Criticality of the request, date needed The applicable statuses are: initiated, evaluated, and accepted. | Software Implementation Customer Project Management |
| 3. | Correction Register | Identifies activities established to correct a deviation or problem concerning the accomplishment of a plan. It may have the following characteristics: - Identifies the initial problem - Defines a solution - Identifies correction actions taken - Identifies the ownership for completion of defined actions - Identifies the open date and target closure date - Contains a status indicator Indicates follow up actions | Project Management |
| 4 | Meeting Record | Records the agreements established with Customer and/or Work Team. It may have the following characteristics: - Purpose of meeting - Attendees - Date, place held - Reference to previous minutes - What was accomplished - Identifies issues raised - Any open issues - Agreements - Next meeting, if any. - The applicable status is: updated. | Project Management |
| 5 | Project Plan | Presents how the project processes and activities will be executed to assure the project’s successful completion, and the quality of the deliverable products. It Includes the following elements which may have the characteristics as follows: - Product Description - Purpose - General Customer requirements - Scope description of what is included and what is not - Objectives of the project - Deliverables - list of products to be delivered to Customer - Tasks, including verification, validation and reviews with Customer and Work Team, to assure the quality of work products. Tasks may be represented as a Work Breakdown Structure (WBS) - Estimated Duration of tasks - Resources (humans, materials, standards, equipment and tools) including the required training, and the schedule when the Resources are needed) - Composition of Work Team - Schedule of the Project Tasks, the expected start and completion date for each task, and the relationship and dependencies of the Tasks - Estimated Effort and Cost - Identification of Project Risks - Version Control Strategy - Product repository tools or mechanism identified - Location and access mechanisms for the - repository specified - Version identification and control defined - Backup and recovery mechanisms defined - Storage, handling and delivery (including archival and retrieval) mechanisms specified - Delivery Instructions - Elements required for product release identified (i.e., hardware, software, documentation etc.) - Delivery requirements - Sequential ordering of Tasks to be performed - Applicable releases identified - Identifies all delivered Software Components with version information - Identifies any necessary backup and recovery procedures The applicable statuses are: verified, accepted, updated and reviewed. | Project Management |
| 6 | Progress Status Record | Records the status of the project against the Project Plan. It may have the following characteristics: - Status of actual Tasks against planned Tasks - Status of actual results against established Objectives / goals - Status of actual resource allocation against planned Resources - Status of actual cost against budget estimates - Status of actual time against planned schedule - Status of actual risk against previously identified - Record of any deviations from planned Tasks and reason why - The applicable status is: evaluated | Project Management |
| 7 | Project Repository | Electronic container to store project work products and deliveries. It may have the following characteristics: - Stores project work products - Stores released Deliverables products - Storage and retrieval capabilities - Ability to browse content - Listing of contents with description of attributes - Sharing and transfer of work products between affected groups - Effective controls over access - Maintain work products descriptions - Recovery of archive versions of work products - Ability to report work products status - Changes to work products are tracked to Change Requests The applicable status is: recovered and updated | Project Management |
| 8 | Project Repository Backup | - Repository used to backup the Project Repository and, if necessary, to recover the information. | Project Management |
| 9 | Resources | Description of human resources, infrastructure and budget assigned to the project | Project Management |
| 10 | Software Configuration | A uniquely identified and consistent set of software products including: - Requirements Specification - Software Design - Traceability Record - Software Components - Software - Test Cases and Test Procedures - Test Report - Product Operation Guide - Software User Documentation - Maintenance Documentation The applicable statuses are: delivered and accepted. | Software Implementation |
| 11 | Statement of Work | Description of work to be done related to Software development. It may Include: - Product Description - Purpose - General Customer requirements - Scope description of what is included and what is not - Objectives of the project - Deliverables list of products to be delivered to Customer - The applicable status is: reviewed | Customer |
| 12 | Validation Results | Documents the validation execution. It may include the record of: - Participants - Date - Place - Duration - Validation check-list - Passed items of validation - Failed items of validation - Pending items of validation Defects identified during validation | Software Implementation |
| 13 | Verification Results | Documents the verification execution. It may include the record of: - Participants - Date - Place - Duration - Verification check-list - Passed items of verification - Failed items of verification - Pending items of verification Defects identified during verification | Software Implementation |

## Artefact Description

This is an alphabetical list of the artifacts that could be produced to facilitate the documentation of a project. The artifacts are not required by Part 5, they are optional.

| Artefacts | Definition |
| --- | --- |
| Project Plan | A statement of how and when a project's objectives are to be achieved, by showing the major products, milestones, activities and resources required on the project. |
| Project Description | A high level description of the project to include; Scope; Objectives and major Deliverables. |
| Project Status Record | Record of the status of the project against the Project Plan. Typical contents include: - status of actual tasks against planned tasks - status of actual results against established objectives / goals - status of actual resource allocation against planned resources - status of actual cost against budget estimates - status of actual time against planned schedule - status of actual risk against previously identified - Record of any deviations from planned tasks and reason why |
| Change Requests | A document describing a new or revised requirement from the customer. |
| Software | A consistent set of software products which include: - Requirements Specification - Software Design - Software (unit, product, item) - Test Cases, Procedures and Incident Reports - Operational Manual - User Manual |
| Acceptance document | Document establishing the customer acceptance of the deliverables established on the project. |
| Project closure report | A document capturing the lessons learned |

# 5. Template

The following templates are provided with this deployment package. Choose and customize them to your project.

Work Breakdown Structure (WBS)

This can be used in an Excel spreadsheet, for example as;

| Task Number | Type of Task | Description of Task | Associated Deliverables | Estimation (person days) |
| --- | --- | --- | --- | --- |

Partial example of WBS

| Task Number | Type of Task | Description of Task | Estimation (person days) |
| --- | --- | --- | --- |
| 1 | Main task | Requirements | 10 |
| 1.1 | Sub-task | Domain analysis | 5 |
| 1.2 | Sub-task | Requirements Identification | 2 |
| 1.3 | Sub-task | Requirements Verification & Validation | 3 |
| 2 | Main task | System Design | 15 |
| 2.1 | Sub-task | Architecture design | 10 |
| 2.2 | Sub-task | Detailed design | 5 |
| 3 | Main task | System Implementation | 30 |
| 3.1 | Sub-task | Code | 25 |
| 3.2 | Sub-task | Testing | 5 |

Partial example of graphical WBS

Sample Project Status Template

| Project Status Report Card |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Submitted by: ____________ |  |  |  | Date submitted (yy-mm-dd): ____________ |  |  |  |
| Reporting period From (yy-mm-dd):______________ To (yy-mm-dd):____________ |  |  |  |  |  |  |  |
| Progress on planned tasks during this reporting period |  |  |  |  |  |  |  |
| Task ID | Task Name | Scheduled start date (yy-mm-dd) | Scheduled end date (yy-mm-dd) |  | % complete | Status (Green, Yellow, Red) | Comment |
| Details of variance: |  |  |  |  |  |  |  |
| Details of proposed corrective actions (if appropriate) |  |  |  |  |  |  |  |
| Project Manager Signoff: ___________________ Date (yy-mm-dd):___________________ |  |  |  |  |  |  |  |

Project Plan – Sample Table of Contents

1 Introduction 1.1 Project Overview A high-level overview of the project to include project objectives; list of the members of the Team; and relationship (if any) to prior/existing projects. 1.2 Project Deliverables A list of the items (e.g. documentation, code) to be delivered. 2 Project Organisation 2.1 Process Model A description of the process to be employed for the Project. 2.2 Project Responsibilities An identification of the roles and specific responsibilities to be adopted by each member of the Project Team. 2.3 Change Control Procedures A description of how change will be handled. 2.4 Configuration Management A description of how configuration management will be implemented. 3 Project Management Process 3.1 Monitoring and Control Mechanisms A description of the methods to be used for monitoring progress and controlling the procedures that will be employed. 3.2 Risk Management A description of main risks and risk mitigation strategy. 4 Work Packages, Schedule, and Budget 4.1 Work Packages Description of the WBS and deliverables. 4.2 Resource The allocation of resources to the tasks. 4.3 Schedule Showing planned starting and finishing dates of each task listed and milestone. 4.4 Budget Project financial plan

# 6. Example

Disclaimer : This section provides, for this topic, a graphical representation of a lifecycle. The example is provided to help the reader implement his own lifecycle fitting his IT project’s context and constraints.

### Example of Project Management Practices Lifecycle

This is only an example – use SPEM stencil for Microsoft Visio (http://www.pa.icar.cnr.it/cossentino/FIPAmeth/docs/SPEM.vss ) in order to produce such a diagram.

Figure 2 Example of Project Management Practices

# 7. Checklist

## Project Plan Review Checklist

Adapted from: Gilb, T., Graham, D., Software Inspection, Addison-Wesley, 1993.

| PP 1 (Objectives) | Plan states the objectives of the project, with reference to business needs |
| --- | --- |
| PP 2 (WBS) | Plan contains the Work Breakdown Structure (WBS) for all tasks. |
| PP 3 (Dependencies) | Plan includes the dependencies between WBS tasks and highlight the critical path |
| PP 4 (Resources) | All resources are specified. |
| PP 5 (Training) | All training needs are identified. |
| PP 6 (Schedule) | Plan includes the schedule for all tasks, and who will perform them. |
| PP 7 (Contingency) | Plan includes a contingency of at least 15%. |
| PP 8 (Deliverables) | Plan specifies all the deliverables and the required format. |
| PP 9 (Approval) | Plan is approved by the relevant manager with responsibility for the project. |

# 8. Tool

There are a great many Software Project Management tools available both Free/Open Source and Proprietary, standalone and on-line (web based), with a wide variety of functionality. A good informal comparison of such tools is available as a link from the Wikipedia ‘Project management software’ site:

http://en.wikipedia.org/wiki/Comparison_of_project_management_software

The two primary uses of Software Project Management software are Scheduling and Providing project status information. The typical features that are useful include:

- Scheduling - One of the most common tasks is to schedule a series of events (tasks, deliverables, milestones), and the complexity of this task can vary considerably depending on how the tool is used. Some common challenges include:

  - Events which depend on one another in different ways or dependencies

  - Scheduling people to work on, and resources required by, the various tasks commonly termed resource scheduling

  - Dealing with uncertainties in the estimates of the duration of each task

  - Arranging tasks to meet various deadlines

  - Juggling multiple projects simultaneously to meet a variety of requirements

- Providing project status information - Project planning software needs to provide a lot of information to various people, to justify the time spent using it. Typical requirements might include:

  - Tasks lists for people, and allocation schedules for resources

  - Overview information on how long tasks will take to complete

  - Early warning of any risks to the project

  - Information on workload, for planning holidays

  - Historical information on how projects have progressed, and in particular, how actual and planned performance are related

  - Optimum utilization of available resource

# 9. Reference to Other Standards and Models

This section provides references of this deployment package to selected ISO and ISO/IEC Standards and to the Capability Maturity Model IntegrationSM version 1.2 of the Software Engineering Institute (CMMI®).

Notes:

- This section is provided for information purpose only.

- Only tasks covered by this Deployment Package are listed in each table.

- The tables use the following convention:

- Full Coverage =  F

- Partial Coverage =  P

- No Coverage = N

## ISO 9001 Reference Matrix

| Title of the Task and Step | Coverage F/P/N | Clause of ISO 9001 | Comments |
| --- | --- | --- | --- |
| To be completed |  |  |  |

## ISO/IEC 12207 Reference Matrix

| Title of the Task and Step | Coverage F/P/N | Clause of ISO/IEC 12207 | Comments |
| --- | --- | --- | --- |
| To be completed |  |  |  |

## CMMI Reference Matrix

| Title of the Task and Step | Coverage F/P/N | Objective/ Practice of CMMI V1.2 | Comments |
| --- | --- | --- | --- |
| To be completed |  |  |  |

# 10. References

| Key | Reference |
| --- | --- |
| [ISO/IEC 12207] | ISO/IEC 12207:2008 Systems and software engineering - Software life cycle processes. |
| [ISO/IEC 24765] | ISO/IEC 24765, Systems and Software Engineering Vocabulary. |
| [ISO/IEC 29110] | Software Engineering — Lifecycle Profiles for Very Small Entities (VSEs) — Part 5-1-2: Management and Engineering Guide - Basic VSE Profile |
| [Dalcher07] | Successful IT Projects, D. Dalcher & L. Brodie, Thomson, 2007 |
| [Jalote02] | Software Project Management in Practice, P. Jalote, Addison-Wesley, 2002 |
| [Jones04] | Software Project Management Practices: Failure Versus Success, C. Jones, CrossTalk, October 2004. |
| [PMBOK13] | Guide to the Project Management Body of Knowledge, Project Management Institute, 2013 accessible from www.pmi.org |
| [Putnam97] | Industrial Strength Software: Effective Management Using Measurement, L. H. Putnam and W. Myers, IEEE, 1997. |
| [Sommerville06] | Software Engineering (8 ed), I. Sommerville, Addison-Wesley, 2006 |

# 11. Evaluation Form

Deployment Package: Project Management V1.3 Your feedback will allow us to improve this deployment package, your comments and suggestions are welcomed.

1. How satisfied are you with the CONTENT of this deployment package?  Very Satisfied  Satisfied  Neither Satisfied nor Dissatisfied  Dissatisfied  Very Dissatisfied

2. The sequence in which the topics are discussed, are logical and easy to follow?  Very Satisfied  Satisfied  Neither Satisfied nor Dissatisfied  Dissatisfied  Very Dissatisfied

3. How satisfied were you with the APPEARANCE/FORMAT of this deployment package?  Very Satisfied  Satisfied  Neither Satisfied nor Dissatisfied  Dissatisfied  Very Dissatisfied

4. Have any unnecessary topics been included? (please describe)

5. What missing topic would you like to see in this package? (please describe) - Proposed topic: - Rationale for new topic

6. Any error in this deployment package? - Please indicate: - Description of error : - Location of error (section #, figure #, table #) :

7. Other feedback or comments:

8. Would you recommend this Deployment package to a colleague from another VSE?  Definitely  Probably  Not Sure  Probably Not  Definitely Not

Optional

- Name:

- e-mail address : __________________________________

Email this form to: claude.y.laporte@etsmtl.ca or Avumex2003@yahoo.com.mx

Roles are defined in a next section. Roles are also defined in ISO/IEC 29110 Part 5-1

Roles are defined in a next section. Roles are also defined in ISO/IEC 29110 Part 5-1

SM CMM Integration is a service mark of Carnegie Mellon University.

® Capability Maturity Model, CMMI are registered in the U.S. Patent and Trademark Office by Carnegie Mellon University.