Deployment Package Verification and Validation (V&V)

Basic Profile

Notes:

This document is the intellectual propriety of its author’s organization. However, information contained in this document is free of use. The distribution of all or parts of this document is authorized for non commercial use as long as the following legal notice is mentioned:

© École de Technologie Supérieure

Commercial use of this document is strictly forbidden. This document is distributed in order to enhance exchange of technical and scientific information.

This material is furnished on an “as-is” basis. The author(s) make(s) no warranties of any kind, either expressed or implied, as to any matter including, but not limited to, warranty of fitness for purpose or merchantability, exclusivity, or results obtained from use of the material.

The processes described in this Deployment Package are not intended to preclude or discourage the use of additional processes that Very Small Entities may find useful.

| Author | Edgardo Palza-Vargas – École de Technologie Supérieure (ETS), (Canada) |
| --- | --- |
| Editors | C. Y. LAPORTE – École de Technologie Supérieure (ETS), (Canada) ANA VAZQUEZ – 5th level, (México) |
| Creation date | 27 July 2009 |
| Last update | 31 July 2009 |
| Version | 0.2 |

Version History

| Date (yyyy-mm-dd) | Version | Description | Author |
| --- | --- | --- | --- |
| 2009-07-27 | 0.1 | Initial version | Edgardo Palza |
| 2009-07-31 | 0.2 | Overall editing | Claude Laporte |
| 2009-08-12 | 0.3 | Update document | Edgardo Palza |

Abbreviations/Acronyms

| Abre./Acro. | Definitions |
| --- | --- |
| DP | Deployment Package - a set of artefacts developed to facilitate the implementation of a set of practices, of the selected framework, in a Very Small Entity. |
| VSE | Very Small Entity – an enterprise, organization, department or project having up to 25 people. |
| VSEs | Very Small Entities |
| V&V | Verification and Validation |

Table of Contents

1. Technical Description	4

Purpose of this document	4

Why is Verification and Validation Important ?	4

Tailoring this Deployment Package	4

2. Definitions	5

Generic Terms	5

Specific Terms	5

3. Relationships with ISO/IEC 29110	7

4. Description of Processes, Activities, Tasks, Steps, Roles and Products	10

Verification & Validation of the Project Plan	10

Analysis and Evaluation of the Change Request for the Project	11

Evaluation the performance of the Project Plan	12

Verification & Validation of the Requirement Specification	14

Verification of Design, Test Cases and Test Procedures	15

Verify Software Construction	17

Software Test for Integration	17

Verification of Maintenance Documentation	18

Role Description	20

Product & Artefacts Descriptions	21

5. Templates	27

6. Example	29

7. Checklist	30

8. Tools	31

9. References to Other Standards and Models	35

ISO 9001 Reference Matrix	35

ISO/IEC 12207 Reference Matrix	35

CMMI Reference Matrix	35

10. References	36

11. Evaluation Form	37

# 1. Technical Description

## Purpose of this document

This Deployment Package (DP) supports the Basic Profile as defined in ISO/IEC 29110 Part 5-1: Management and Engineering Guide. A DP is a set of artefacts developed to facilitate the implementation of a set of practices in a Very Small Entity (VSE). A DP is not a process reference model (i.e. it is not prescriptive). The elements of a typical DP are: description of processes, activities, tasks, roles and products, template, checklist, reference to standards, etc.

Information contained in this DP is applicable to VSEs that do not develop critical software, commercial off the shelf software products. For a project with intensive verification and validation (V&V) activities, the use of the appropriate standards and guides are recommended (ex. IEEE 1012, DO-178B, etc.)

The content of this document is entirely informative.

This document has been produced by Edgardo Palza a graduate from the software engineering program of ÉTS (École de Technologie Supérieure - www.etsmtl.ca).

## Why is Verification and Validation Important ?

Computers and Telecommunications affect our lives and software is everywhere in our daily life (e.g. cars, aircraft, medical devices, and nuclear power plants, etc.). It is clear that software projects have become increasingly sophisticated, more complex and higher demands for reliability and safety (Dettmer 1988). Software development requires a set of activities and task to make sure that the VSE has built the right product and the product developed is built right.

## Tailoring this Deployment Package

If a VSE has already implemented, in its processes, all the verification and validation activities (V&V) and tasks described in this DP, the VSE can skip this DP.

If a VSE has not implemented, in its processes, all the verification and validation activities (V&V) and tasks described in this DP, it may use this DP to add the missing activities and tasks.

# 2. Definitions

In this section, the reader will find two sets of definitions. The first set defines the terms used in all Deployment Packages, i.e. generic terms. The second set of terms used in this Deployment package, i.e. specific terms.

## Generic Terms

Process: set of interrelated or interacting activities which transform inputs into outputs [ISO/IEC 12207].

Activity: a set of cohesive tasks of a process [ISO/IEC 12207].

Task: required, recommended, or permissible action, intended to contribute to the achievement of one or more outcomes of a process [ISO/IEC 12207].

Sub-Task: When a task is complex, it is divided into sub-tasks.

Step: In a deployment package, a task is decomposed in a sequence of steps.

Role: a defined function to be performed by a project team member, such as testing, filing, inspecting, coding. [ISO/IEC 24765]

Product: piece of information or deliverable that can be produced (not mandatory) by one or several tasks. (e. g. design document, source code).

Artefact: information, which is not listed in ISO/IEC 29110 Part 5, but can help a VSE during the execution of a project.

## Specific Terms

Audit: an independent examination of a software product, software process, or set of software processes performed by a third party to assess compliance with specifications, standards, contractual agreements, or other criteria [IEEE 1028].

NOTE—An audit should result in a clear indication of whether the audit criteria have been met.

Correction: action to eliminate a detected nonconformity

NOTE A correction can be, for example, rework or regrade [ISO 29110].

Customer: organization or person that receives a product

NOTE   acquirer or user is customer [ISO 9000]

Inspection: a visual examination of a software product to detect and identify software anomalies, including errors and deviations from standards and specifications.

NOTE—Inspections are peer examinations led by impartial facilitators who are trained in inspection techniques. Determination of remedial or investigative action for an anomaly is a mandatory element of a software inspection, although the solution should not be determined in the inspection meeting [IEEE 1028].

Life cycle: the evolution of a system, product, service, project or other human-made entity from conception through retirement. [ISO/IEC 12207:2008 and ISO/IEC 15288:2008]

Management review: A systematic evaluation of a software product or process performed by or on behalf of management that monitors progress, determines the status of plans and schedules, confirms requirements and their system allocation, or evaluates the effectiveness of management approaches used to achieve fitness for purpose [IEEE 1028].

Report: describe the results of activities such as investigations, assessments, and tests [ISO/IEC 15289]

Review: a process or meeting during which a software product, set of software products, or a software process is presented to project personnel, managers, users, customers, user representatives, auditors or other interested parties for examination, comment or approval [IEEE 1028].

Technical review: a systematic evaluation of a software product by a team of qualified personnel that examines the suitability of the software product for its intended use and identifies discrepancies from specifications and standards [IEEE 1028].

NOTE—Technical reviews may also provide recommendations of alternatives and examination of various alternatives.

Validation: confirmation, through the provision of objective evidence that the requirements for a specific intended use or application have been fulfilled [ISO 9000:2005].

NOTE Validation in a life cycle context is the set of activities ensuring and gaining confidence that a system is able to accomplish its intended use, goals and objectives.

Verification: confirmation, through the provision of objective evidence that specified requirements have been fulfilled [ISO 9000:2005]

NOTE Verification in a life cycle context is a set of activities that compares a product of the life cycle against the required characteristics for that product. This may include, but is not limited to, specified requirements, design description and the system itself.

Walk-through: a static analysis technique in which a designer or programmer leads members of the development team and other interested parties through a software product, and the participants ask questions and make comments about possible anomalies, violation of development standards, and other problems [IEEE 1028].

# 3. Relationships with ISO/IEC 29110

This deployment package covers the activities related to V&V of the ISO Technical Report ISO/IEC 29110 Part 5-1 for Very Small Entities (VSEs) – Basic Profile [ISO/IEC29110].

In this section, the reader will find a list of Project Management (PM) and Software Implementation (SI) process, activities, tasks and roles that are directly related to V&V.

- Process: 4.2 Project Management (PM)

- Activity: PM 4.2.8.1 Project planning

- Tasks:

| PM.1.13 Verification of the Project Plan. Verify that all Project Plan elements are viable and consistent. The results found are documented in a Verification Results and corrections are made until the document is approved by TL. | PM TL |
| --- | --- |
| PM.1.14 Validation of the Project Plan. Validate that the Project Plan elements definition match with the Statement of Work. The results found are documented in a Validation Results and corrections are made until the document is approved by CUS. | PM CUS |

- Activity: PM 4.2.8.2 Project plan execution

- Tasks:

| Tasks | Roles |
| --- | --- |
| PM.2.2 Analyze and evaluate the Change Request for cost, schedule and technical impact, and include the accepted changes in the Project Plan. The Change Request can be initiated externally by the Customer or internally by the Work Team. The evaluation of Change Request initiated by Customer or those which affects the Customer needs. Negotiate with Customer to obtain its acceptance (see PM.2.4). | PM TL |

- Activity: PM 4.2.8.3 Project assessment and control

- Tasks:

| Tasks | Roles |
| --- | --- |
| PM.3.1 Evaluate project progress with respect to the Project Plan, comparing: - actual tasks against planned tasks - actual results against established project objectives - actual resource allocation against planned resources - actual cost against budget estimates - actual time against planned schedule - actual risk against previously identified | PM TL WT |

- Process: 4.3 Software Implementation (SI) process

- Activity: 4.3.8.2 SI.2 Software requirements analysis

- Tasks:

| Tasks | Roles |
| --- | --- |
| SI.2.3 Verification of the Requirements Specification. Verify the correctness and testability of the Requirements Specification and its consistency with the Product Description. Additionally, review that requirements are complete, unambiguous and not contradictory. The results found are documented in a Verification Results and corrections are made until the document is approved by AN. If significant changes were needed, initiate a Change Request. | AN |
| SI.2.4 Validation of the Requirements Specification Validate that Requirements Specification satisfies needs and agreed upon expectations, including the user interface usability. The results found are documented in a Validation Results and corrections are made until the document is approved by CUS. | CUS AN |

- Activity: 4.3.8.3 SI.3 Software architectural and detailed design

- Tasks:

| Tasks | Roles |
| --- | --- |
| SI.3.4 Verification of the Software Design Verify correctness of Software Design documentation, its feasibility and consistency with their Requirement Specification. Verify that the Traceability Record contains the adequate relationships between requirements and the Software Design elements. The results found are documented in a Verification Results and corrections are made until the document is approved by AN. If significant changes were needed, initiate a Change Request. | AN DES |
| SI.3.6 Verification of the Test Cases and Test Procedures. Verify consistency among Requirements Specification, Software Design and Test Cases and Test Procedures. The results found are documented in a Verification Results and corrections are made until the document is approved by AN. | DES AN |

- Activity: 4.3.8.4 SI.4 Software construction

- Tasks:

| Tasks | Roles |
| --- | --- |
| SI.4.4 Apply unit test cases to verify that functions work accordingly to the detailed part of the Software Design. | PR |

- Activity: 4.3.8.5 SI.5 Software integration and tests

- Tasks:

| Tasks | Roles |
| --- | --- |
| SI.5.4 Perform tests using Test Cases and Test Procedures for integration and document results in Test Report. | PR CUS |

- Activity: 4.3.8.6 SI.6 Product delivery

- Tasks:

| Tasks | Roles |
| --- | --- |
| SI.6.4 Verification of the Maintenance Documentation. Verify consistency of Maintenance Documentation with Software Configuration. The results found are documented in a Verification Results and corrections are made until the document is approved by DES. | DES |

# 4. Description of Processes, Activities, Tasks, Steps, Roles and Products

Process: 4.2 Project Management (PM)

The purpose of the Project Management process is to establish and carry out in a systematic way the tasks of the software implementation project, which allows complying with the project’s objectives in the expected quality, time and costs.

Activity: PM 4.2.8.1 Project planning

The Project Planning activity documents the planning details needed to manage the project

- PM.1.13 Verification of the Project Plan.

Verify that all Project Plan elements are viable and consistent.

- PM.1.14 Validation of the Project Plan.

Validate that the Project Plan elements definition match with the Statement of Work.

## Verification & Validation of the Project Plan

| Objectives: | Verify all Project Plan elements and validate if elements match with the Statement of Work. |
| --- | --- |
| Rationale: | In order to accomplish project objectives in the expected quality, time and cost, it is important to verify and validate all project elements. |
| Roles: | Project Manager |
|  | Technical Leader |
|  | Customer |
| Products: | Verification Results |
|  | Acceptance Record |
| Artefacts: | Project Plan |
|  | Statement of Work |
| Steps: | 1. Verify the Project Plan |
|  | 2. Validate the Project Plan |
|  | 3. Document the results |
|  | 4. Make corrections |
| Step Description: | Step 1. Verify that all Project Plan Verify that all Project Plan elements are viable and consistent Step 2. Validate the Project Plan Validate that the Project Plan elements definition match with the Statement of Work. Step 3. Document the results Document the results of verification in Verification Results Step 4. Make corrections Make corrections until the document is approved (by TL or CUS) Note: Very that the Project Plan including V&V tasks in order to assure the quality of work products. |

Activity: PM 4.2.8.2 Project plan execution

The Project Plan Execution activity implements the documented plan on the project.

- PM.2.2 Analyze and evaluate the Change Request for cost, schedule and technical impact, and include the accepted changes in the Project Plan.

## Analysis and Evaluation of the Change Request for the Project

| Objectives: | To manage Project Plan changes according with a process agreed upon with the customer. |
| --- | --- |
| Rationale: | Project Plan changes must be planned and agreed upon with the customer on the project. |
| Roles: | Project Manager |
|  | Customer |
|  | Technical Leader |
| Products: | Project Plan |
|  | Acceptance Record |
| Artefacts: | Change Requests |
|  | Progress Status Record |
| Steps: | 1. Analyze the Change |
|  | 2. Evaluate the Change |
|  | 3. Prioritize changes |
|  | 4. Approve changes |
|  | 5. Include changes |
| Step Description: | Step 1. Analyze the Change - Perform an impact analysis of changes on the project in term of cost, schedule and technical considerations. Step 2. Evaluate the Change - Estimate the impact of changes in terms of cost, schedule and technical side. Step 3. Prioritize changes - The project manager must obtain from the customer a prioritization of the identified Step 4. Approve changes - Obtain customer sign-off on agree change. Step 5. Include changes - Include the prioritized and accepted changes in the Project Plan. |

Activity: PM 4.2.8.3 Project assessment and control

The Project Assessment and Control activity monitors and evaluates the performance of the plan against documented commitments.

- PM.3.1 Evaluate project progress with respect to the Project Plan

## Evaluation the performance of the Project Plan

| Objectives: | The purpose of the Evaluation of the performance of the Project Plan is to determine the status of the project and ensure that the project performs according to plans and schedules, within projected budgets and it satisfies technical objectives. |
| --- | --- |
| Rationale: | This task shows how a Project Plan should be assessed in terms of planned activities identified at the project planning phase versus actual project progress. |
| Roles: | Project Manager |
|  | Technical Leader |
|  | Work Team |
| Products: | Project Plan |
|  | Progress Status Record |
| Artefacts: | Project Plan |
|  | Progress Status Record |
| Steps: | - Evaluate project |
|  | - Record the Progress Status |
| Step Description: | Step 1. Evaluate project, in terms of: - Actual tasks against planned tasks - Actual results against established project objectives - Actual resource allocation against planned resources - Actual cost against budget estimates - Actual time against planned schedule - Actual risk against previously identified Step 2. Record the Progress Status of the Project A record actual project data in should be maintained in a Progress Status Record where the status of an item is typically recorded according to the ‘traffic light’ system: - Green - as ‘on target’ - Amber - as ‘not on target but recoverable’ - Red - as ‘not on target and recoverable only with difficulty’ |

Process: 4.3 Software Implementation (SI) process

The purpose of the Software Implementation process is the systematic performance of the analysis, design, construction, integration and tests activities for new or modified software products according to the specified requirements.

Activity: 4.3.8.2 SI.2 Software requirements analysis

The Software Requirements Analysis activity analyzes the agreed customer’s requirements and establishes the validated project requirements.

- SI.2.3 Verification of the Requirements Specification.

Verify the correctness and testability of the Requirements Specification and its consistency with the Product Description. Additionally, review that requirements are complete, unambiguous and not contradictory.

- SI.2.4 Validation of the Requirements Specification

Validate that Requirements Specification satisfies needs and agreed upon expectations, including the user interface usability.

## Verification & Validation of the Requirement Specification

| Objectives: | Verify requirements and obtain validation from the customer or his representative. |
| --- | --- |
| Rationale: | In order to avoid constant fundamental changes in the requirements, it is important to ask for the requirement validation from the customer. |
| Roles: | Analyst |
|  | Customer |
| Products: | Requirements Document |
|  | Verification Results |
|  | Acceptance Record |
| Artefacts: | Requirements Document |
| Steps: | 1. Verify the Requirements Specification |
|  | 2. Document Results |
|  | 3. Make Corrections |
|  | 4. Initiate a Change Request (as necessary) |
|  | 5. Validate Requirements Specification |
| Step Description: | Step 1. Verify the Requirements Specification for: - Correctness and testability - Consistency with the Product Description - Complete, unambiguous and not contradictory Step 2. Document Results. - Document results of verification in Verification Results Step 3. Make Corrections. - Make corrections until the document is approved by AN or CUS. Step 4. Initiate a Change Request (as necessary) - Identify purpose of the Change Request - Document the impact of Change (high level) - Identify the critically of the Change Step 5. Validate Requirements Specification - Obtain from your customer an approval of the requirements (or of a given subset if you are using an iterative lifecycle). |

Activity: 4.3.8.3 SI.3 Software architectural and detailed design

The Software Architectural and Detailed Design activity transforms the software requirements to the system software architecture and software detailed design.

- SI.3.4  Verification of the Software Design

Verify correctness of Software Design documentation, its feasibility and consistency with their Requirement Specification. Verify that the Traceability Record contains the adequate relationships between requirements and the Software Design elements.

- SI.3.6 Verification of the Test Cases and Test Procedures.

Verify consistency among Requirements Specification, Software Design and Test Cases and Test Procedures.

## Verification of Design, Test Cases and Test Procedures

| Objectives: | To verify that Software Architecture and Detail Design are correct, consistent and feasible according with the Requirement Specification |
| --- | --- |
| Rationale: | In order to avoid lack of consistency, feasibility, correctness, traceability between Software Architectural and Design and the Requirements Specifications a set of verification tasks are recommend to be implemented in the project |
| Roles: | Analyst |
|  | Designer |
| Products: | Verification Results |
|  | Acceptance Record |
|  | Change Request (if necessary) |
| Artefacts: | Software Design documentation |
|  | Requirements Specification |
|  | Traceability Record |
|  | Test Cases and Test Procedures |
| Steps: | 1. Very the Software Design documentation |
|  | 2. Verify the Traceability Record |
|  | 3. Verify the Test Cases and Test Procedures |
|  | 4. Verify consistency |
|  | 5. Document Results |
|  | 6. Make Corrections |
|  | 7. Initiate a Change Request (if necessary) |
| Step Description: | Step 1. Very the Software Design documentation for: - Correctness - Feasibility and consistency Step 2. Verify the Traceability Record - Verify that the Traceability Record contains the adequate relationships between requirements and the Software Design elements. Step 3. Verify the Test Cases and Test Procedures - Verify consistency among Requirements Specification, Software Design and Test Cases and Test Procedures. Step 4. Verify consistency - Verify consistency among Requirements Specification Step 5. Document Results. - Document results of verification in Verification Results, Software Design and Test Cases and Test Procedures. Step 6. Make Corrections. - Make corrections until the document is approved by DES /AN. Step 7. Initiate a Change Request (as necessary) - Identify purpose of the Change Request - Document the impact of Change (high level) - Identify the critically of the Change |

Activity: 4.3.8.4 SI.4 Software construction

The Software Construction activity develops the software code and data from the Software Design.

- SI.4.4 Apply unit test cases to verify that functions work accordingly to the detailed part of the Software Design.

## Verify Software Construction

| Objectives: | Verify Software functions using test cases |
| --- | --- |
| Rationale: | To assure that key functions identified in the Requirements Specifications have been implemented according to Software Design |
| Roles: | Programmer |
| Products: | Software Component |
|  | Verification Results |
| Artefacts: | Software Design |
|  | Software Component |
|  | Test cases and Procedures |
| Steps: | 1. Identify Software Component |
|  | 2. Apply unit test |
| Step Description: | Step 1. Identify Software Component - Identify unit of code and data to be tested Step 2. Apply Unit Test - Verify using Test Cases and Procedures if software component works according to Software Design |

Activity: 4.3.8.5 SI.5 Software integration and tests

The Software Integration and Test activity ensures that the integrated software components satisfy the software requirements.

- SI.5.4 Perform tests using Test Cases and Test Procedures for integration and document results in Test Report.

## Software Test for Integration

| Objectives: | To verify that software components are integrated and satisfy software requirements |
| --- | --- |
| Rationale: | To assure that Software Components are integrated and defects are documented the Test Report. |
| Roles: | Programmer |
|  | Customer |
| Products: | Software Component |
|  | Test Report |
| Artefacts: | Software Component |
|  | Test Report |
|  | Requirements Specification |
|  | Test Cases and Test Procedures |
| Steps: | 1. Identify Integrated Software Component |
|  | 2. Perform test integration |
|  | 2. Document Results |
| Step Description: | Step 1. Identify Integrated Software Component - Identify integrated code and data to be tested Step 2. Perform Test Integration - Perform tests using Test Cases and Test Procedures for integration Step 3. Document Results - Document results of Test Integration in the Test Report. |

Activity: 4.3.8.6 SI.6 Product delivery

The Product Delivery activity provides the integrated software product to the Customer.

- SI.6.4 Verification of the Maintenance Documentation.

Verify consistency of Maintenance Documentation with Software Configuration.

## Verification of Maintenance Documentation

| Objectives: | The purpose of this task is verifying the consistency of the Configuration Item related to Maintenance Documentation with the Software Configuration Database. Any change in the configuration Item should be registered in the Database according to a documented procedure in the corresponding DP. |
| --- | --- |
| Rationale: | Verify that Maintenance Documentation and Software version are consistent and ready for delivery. |
| Roles: | Designer |
|  | Technical Leader |
| Products: | Verification Results |
|  | Acceptance Record |
|  | Maintenance Documentation |
| Artefacts: | Software Configuration |
|  | Maintenance Documentation |
|  | Acceptance Record |
| Steps: | 1. Verify consistency of Maintenance Documentation |
|  | 2. Document Results |
|  | 3. Make Corrections |
| Step Description: | Step 1. Verify the Maintenance Documentation. - Verify consistency of Maintenance Documentation with Software Configuration. Step 2. Document Results. - Document results of verification in Verification Results Step 3. Make Corrections. - Make corrections until the document is approved by TL. |

## Role Description

This is an alphabetical list of the roles, abbreviations and required competencies description.

|  | Role | Abbreviation | Competency |
| --- | --- | --- | --- |
| 1. | Analyst | AN | Knowledge and experience eliciting, specifying and analyzing the requirements. Knowledge in designing user interfaces and ergonomic criteria. Knowledge of the revision techniques and experience on the software development and maintenance. Knowledge of the editing techniques and experience on the software development and maintenance. |
| 2. | Customer | CUS | Knowledge of the Customer processes and ability to explain the Customer requirements. The Customer (representative) must have the authority to approve the requirements and their changes. The Customer includes user representatives in order to ensure that the operational environment is addressed. Knowledge and experience in the application domain. |
| 3. | Designer | DES | Knowledge and experience in the software components and architecture design. Knowledge of the revision techniques and experience on the software development and maintenance. Knowledge of the editing techniques and experience on the software development and maintenance. Knowledge and experience in the planning and performance of integration and system tests. |
| 4. | Programmer | PR | Knowledge and/or experience in programming, integration and unit tests. Knowledge of the revision techniques and experience on the software development and maintenance. Knowledge of the editing techniques and experience on the software development and maintenance. |
| 5. | Project Manager | PM | Leadership capability with experience making decisions, planning, personnel management, delegation and supervision, finances and software development. |
| 6. | Technical Leader | TL | Knowledge and experience in the software development and maintenance. |
| 7. | Work Team | WT | Knowledge and experience according to their roles on the project: AN, DES, and/or PR. |

## Product & Artefacts Descriptions

This is an alphabetical list of the input, output and internal process products & artefacts, its descriptions, possible states and the source of the product.

|  | Name | Description | Source |
| --- | --- | --- | --- |
| 1. | Acceptance Record | Document establishing the customer acceptance of the deliverables of the project. It may contain: - Record of the receipt of the delivery - Identifies the date received - Identifies the delivered elements - Records the verification of any Customer acceptance criteria defined - Signed by receiving Customer | Project Management |
| 2. | Change Request | It may has the following characteristics: - Identifies purpose of change - Identifies request status (new, accepted, rejected) - Identifies requester contact information - Impacted system(s) - Impact to operations of existing system(s) defined - Impact to associated documentation defined - Criticality of the request, date needed by The applicable statuses are: initiated, evaluated, accepted. | Software Implementation Customer Project Management |
| 3. | Correction Register | Activities established to correct a deviation or problem concerning the accomplishment of a plan. It may contain: - Identifies the initial problem - Identifies the ownership for completion of defined action - Defines a solution - Identifies the open date and target closure date - Contains a status indicator - Indicates follow up actions | Project Management |
| 4. | Maintenance Documentation | Electronic or printed document describing the Software Configuration and the environment used for development and testing (compilers, design tools, construction and tests). The Maintenance Documentation includes or refers to products developed during implementation such as the Requirements Specification. It is written in terms that maintenance personnel can understand. The applicable statuses are: verified and baselined. | Software Implementation |
| 5. | Meeting Record | Record of the agreements established with Customer and/or Work Team. May address the following: - purpose of meeting - attendees - date, place held - reference to previous minutes - what was accomplished - identifies issues raised - any open issues - agreements - next meeting, if any. The applicable status is: updated. | Project Management |
| 6. | Progress Status Record | Record of the status of the project against the Project Plan. It may contain: - status of actual tasks against planned tasks - status of actual results against established objectives / goals - status of actual resource allocation against planned resources - status of actual cost against budget estimates - status of actual time against planned schedule - status of actual risk against previously identified Record of any deviations from planned tasks and reason why. The applicable status is: evaluated. | Project Management |
| 7. | Project Plan | Includes: - Product Description - Scope - Objectives - Deliverables - Tasks, including verification, validation and reviews with Customer and Work Team, to assure the quality of work products. Tasks may be represented as a Work Breakdown Structure (WBS). - Relationship and Dependence of the Tasks - Estimated Duration of tasks - Resources (humans, materials, equipment and tools) including the required training, and the schedule when the resources are needed. - Composition of Work Team - Schedule of the Project Tasks, the expected start and completion date, for each task. - Estimated Effort and Cost - Identification of Project Risks - Version Control Strategy - Product repository tools or mechanism identified - Location and access mechanisms for the repository specified - Version identification and control defined - Backup and recovery mechanisms defined - Storage, handling and delivery (including archival and retrieval) mechanisms specified - Delivery Instructions - Elements required for product release identified (i.e., hardware, software, documentation etc.) - Delivery requirements - Sequential ordering of tasks to be performed - Applicable releases identified - Identifies all delivered software components with version information - Identifies any necessary backup and recovery procedures The applicable statuses are: verified, validated, changed and reviewed. | Project Management |
| 8. | Requirements Specification | Includes an introduction and a description of the requirements. It may contain: - Introduction –general description of software and its use within the scope of the customer business; - Requirements description: - functionality – established needs to be satisfied by the software when it is used in specific conditions. Functionality must be adequate, accurate and safe. - user interface – definition of those user interface characteristics that allow to understand and learn the software easily so the user be able to perform his/her tasks efficiently including the interface exemplar description; external interfaces – definition of interfaces with other software or hardware; - reliability – specification of the software execution level concerning the maturity, fault tolerance and recovery; - efficiency – specification of the software execution level concerning the time and use of the resources; - maintenance – description of the elements facilitating the understanding and execution of the future software modifications; - portability – description of the software characteristics that allow its transfer from one place to other; - design and construction limitations – needs imposed by the customer; - inter-operability – capability for two or more systems or software components be able to change information each other and use it. - reusability – feature of any product/sub-product, or a part of it, so that it can be used by several users as an end product, in the own software development, or in the execution of other software products. - legal and regulative – needs imposed by laws, regulations, etc. Each requirement is identified, unique and it is verifiable or can be assessed. The applicable statuses are: verified, validated and baselined. | Software Implementation |
| 9. | Software Component | A set of related code units. The applicable statuses are: unit tested, corrected and baselined. | Software Implementation |
| 10. | Software Design | This document includes textual and graphical information on the software structure. This structure may includes the following parts: Architectural High Level Software Design – Describes the overall Software structure: - Identifies the required software Components - Identifies the relationship between software Components - Consideration is given to any required: - software performance characteristics - software interfaces - security characteristics - database design requirements - error handling and recovery attributes Detailed Low Level Software Design – includes details of the software components to facilitate its construction and test within the programming environment; - Provides detailed design (could be represented as a prototype, flow chart, entity relationship diagram, pseudo code, etc.) - Provides format of input / output data - Provides specification of data storage needs - Establishes required data naming conventions - Defines the format of required data structures - Defines the data fields and purpose of each required data element - Provides the specifications of the program structure The applicable statuses are: verified and baselined. | Software Implementation |
| 11. | Statement of Work | It may Include: - Product Description - Scope - Objectives - Deliverables The applicable status is: reviewed | Customer |
| 12. | Test Cases and Test Procedures | Test Case may include: - Identifies the test case - Test items - Input specifications - Output specifications - Environmental needs - Special procedural requirements - Interface dependencies Test Procedures may include: - Identifies: test name, test description and test completion date - Identifies potential implementation issues - Identifies the person who completed the test procedure - Identifies prerequisites - Identifies procedure steps including the step number, the required action by the tester and the expected results The applicable statuses are: verified and baselined. | Software Implementation |
| 13. | Test Report | Documents the tests, it may include: - A summary of each defect - Identifies the related test case - Identifies the tester who found each defect - Identifies the severity for each defect - Identifies the affected function(s) for each defect - Identifies the date when each defect originated - Identifies the date when each defect was resolved - Identifies the person who resolved each defect The applicable status is: baselined. | Software Implementation |
| 14. | Traceability Record | - Identification Number - Text of the need - Text of the Requirement - Phase of the SDLC - Verification Method - Title or ID of test Procedure - Verification date - Name of person that performed the verification - Result of verification | Project Management Software Implementation |
| 15. | Verification Results | May include the record of: - Participants - Date - Place - Duration - Verification check-list - Passed items of verification - Failed items of verification - Pending items of verification - Defects identified during verification | Project Management Software Implementation |

# 5. Templates

- Software Verification plan Template:

http://www.cs.txstate.edu/~js55/SVVPLAN.pdf

- Software Verification plan Template:

http://www.dpi.state.nc.us/docs/techarchitecture/information/sdlc/2/vali dverifyplan.pdf

Software Verification and Validation Plan (SVVP)

Adapted from IEEE 1012

1. Purpose

2. Referenced documents

3. Definitions

4. V&V overview

4.1 Organization

4.2 Master schedule

4.3 Software integrity level scheme

4.4 Resources summary

4.5 Responsibilities

4.6 Tools, techniques, and methods

5. V&V processes

5.1 Process: Management

5.1.1 Activity: Management of V&V

5.2 Process: Acquisition (Optional)

5.2.1 Activity: Acquisition support V&V

5.3 Process: Supply (Optional)

5.3.1 Activity: Planning V&V

5.4 Process: Development

5.4.1 Activity: Concept V&V

5.4.2 Activity: Requirements V&V

5.4.3 Activity: Design V&V

5.4.4 Activity: Implementation V&V

5.4.5 Activity: Test V&V

5.4.6 Activity: Installation and checkout V&V

5.5 Process: Operation

5.5.1 Activity: Operation V&V

5.6 Process: Maintenance

5.6.1 Activity: Maintenance V&V

6. V&V reporting requirements

6.1 Task reports

6.2 Activity summary reports

6.3 Anomaly reports

6.4 V&V final report

6.5 Special studies reports (optional)

6.6 Other reports (optional)

7. V&V Administrative requirements (Optional)

7.1 Anomaly resolution and reporting

7.2 Task iteration policy

7.3 Deviation policy

7.4 Control procedures

7.5 Standards, practices, and conventions

8. V&V test documentation requirements (Optional)

# 6. Example

- Software Verification plan – Example

http://dogbert.mse.cs.cmu.edu/mse2005/projects/Pandora/public_html/index.html

- Software Verification plan – Example

http://www.cs.mu.oz.au/341/2008/Tutorials/svvp.pdf

# 7. Checklist

Review, Inspections, Testing Checklists

- Information should be taken from Construx

http://www.construx.com/Page.aspx?nid=208

# 8. Tools

Comparison of review types – from IEEE 1028

Review & Inspections Process & Methods

- Information should be taken from Karl Wiegers

http://www.processimpact.com/pubs.shtml#pr

Traceability Tool

Requirements traceability should:

|  | - Ensure traceability for each level of decomposition performed on the project. In particular: - Ensure that every lower level requirement can be traced to a higher level requirement or original source - Ensure that every design, implementation, and test element can be traced to a requirement - Ensure that every requirement is represented in design and implementation - Ensure that every requirement is represented in testing/verification - Ensure that traceability is used in conducting impact analysis of requirements changes on project plans, activities and work products - Be maintained and updated as changes occur. - Be consulted during the preparation of Impact Analysis for every proposed change to the project - Be planned for, since maintaining the links/references is a labor intensive process that should be tracked/monitored and should be assigned to a project team member - Be maintained as an electronic document |
| --- | --- |

| Instructions |  |
| --- | --- |
| The above table should be created in a spreadsheet or database such that it may be easily sorted by each column to achieve bi-directional traceability between columns. The unique identifiers (ID) should be assigned in a hierarchical outline form such that the lower level (i.e. more detailed) items can be traced to higher items. |  |
| Identification Number | The Unique Requirement Identification (ID) where the requirement is referenced, and/or the unique identification for decomposed requirements. |
| Text of the need | The original text of the need from the customer |
| Text of the requirement | The text of the requirement |
| Verification Method | The verification method is identified (e.g. Test (T), Demonstration (D), Analysis (A), Simulation (S), Inspection (I)). |
| Title or ID of Use Case | The unique identifier of the Use Case or design component where a requirement is designed. |
| Title or ID of Code Module | The unique identifier of the software module where the design is realized or coded. |
| Verification Date | The date the requirement is verified (e.g. tested) |
| Name of person that performed the verification | The name of the person that performed the verification |
| Result of the verification | Result of verification (i.e. Success (S) or Failure (F)) |

# 9. References to Other Standards and Models

This section provides references of this deployment package to ISO/IEC Standards and to the Capability Maturity Model IntegrationSM for Development version 1.2 of the Software Engineering Institute (CMMI-DEV®).

Notes:

- This section is provided for information purpose only.

- Only tasks covered by this Deployment Package are listed in each table.

- The tables use the following convention:

- Full Coverage =  F

- Partial Coverage =  P

- No Coverage = N

## ISO 9001 Reference Matrix

| Title of the Task and Step | Coverage F/P/N | Clause of ISO 9001 | Comments |
| --- | --- | --- | --- |
| <details> | <details> | <details> |  |

## ISO/IEC 12207 Reference Matrix

| Title of the Task and Step | Coverage F/P/N | Clause of ISO/IEC 12207 | Comments |
| --- | --- | --- | --- |
| <details> | <details> | <details> |  |

## CMMI Reference Matrix

| Title of the Task and Step | Coverage F/P/N | Objective/ Practice of CMMI V1.2 | Comments |
| --- | --- | --- | --- |
| <details> | <details> | <details> |  |

# 10. References

| Key | Reference |
| --- | --- |
| [Dettmer1988] | Dettmer, R. 1988. « Making software safer ». IEE Review, vol. 34, no 8, p. 321-324 |
| [/DO-178B] | RTCA/DO-178B. 1992. « RTCA/DO-178B: Software considerations in airborne systems and equipment certification ». (Dec. 1, 1992.) |
| [IEEE 1012] | IEEE Std 1012. 2004. « IEEE Standard for Software Verification and Validation ». IEEE Std 1012-2004 (Revision of IEEE Std 1012-1998), p. 0_1-110. |
| [IEEE 1028] | IEEE Std 1012. 2008. « IEEE Standard for Software Reviews and Audits». (Revision of IEEE Std 1028-1997). |
| [ISO/IEC 12207] | ISO/IEC 12207:2008 Systems and software engineering - Software life cycle processes. |
| [ISO/IEC 24765] | ISO/IEC 24765, Systems and Software Engineering Vocabulary. |
| [ISO/IEC 29110] | Software Engineering — Lifecycle Profiles for Very Small Entities (VSEs) — Part 5-1: Management and Engineering Guide - Basic VSE Profile |

# 11. Evaluation Form

Deployment Package – Verification and Validation Version 0.2 Your feedback will allow us to improve this deployment package, your comments and suggestions are welcomed.

1. How satisfied are you with the CONTENT of this deployment package?  Very Satisfied  Satisfied  Neither Satisfied nor Dissatisfied  Dissatisfied  Very Dissatisfied

2. The sequence in which the topics are discussed, are logical and easy to follow?  Very Satisfied  Satisfied  Neither Satisfied nor Dissatisfied  Dissatisfied  Very Dissatisfied

3. How satisfied were you with the APPEARANCE/FORMAT of this deployment package?  Very Satisfied  Satisfied  Neither Satisfied nor Dissatisfied  Dissatisfied  Very Dissatisfied

4. Have any unnecessary topics been included? (please describe)

5. What missing topic would you like to see in this package? (please describe) - Proposed topic: - Rationale for new topic

6. Any error in this deployment package? - Please indicate: - Description of error : - Location of error (section #, figure #, table #) :

7. Other feedback or comments:

8. Would you recommend this Deployment package to a colleague from another VSE?  Definitely  Probably  Not Sure  Probably Not  Definitely Not

Optional

- Name:

- e-mail address : __________________________________

Email this form to: claude.y.laporte@etsmtl.ca or Avumex2003@yahoo.com.mx

Source: Prof. Jeff Sloam from Texas State University

Source: Department of Public School of North Caroline

Source : Carnegie Mellon Software Engineering Masters Program studio projects

Source: Melbourne School of Engineering. Department of Computer Science and Software Engineering

http://www.construx.com

www.processimpact.com

SM CMM Integration is a service mark of Carnegie Mellon University.

® Capability Maturity Model, CMMI are registered in the U.S. Patent and Trademark Office by Carnegie Mellon University.