## Assessment Guidelines
Source: ISO/IEC 15504-2 | Source: Varkoi, T., Self-Assessment Deployment Package

## Dashbord
Tasks Execution
Process Name | % Executed | Is implemented | % Point of the 67 tasks | Activity | Fully | Largely | Partially | No
Project Management Activities
| 32.5% | Partially | 7.276% | PM.1 Project Planning | 0 | 0 | 15 | 0
| 32.5% | Partially | 2.91% | PM.2 Project Plan Execution | 0 | 0 | 6 | 0
| 32.5% | Partially | 1.455% | PM.3 Project Assessment and Control | 0 | 0 | 3 | 0
| 32.5% | Partially | 0.9701% | PM.4 Project Closure | 0 | 0 | 2 | 0
Process Average | 32.5% |  |  |  | 0 | 0 | 26 | 0
Software Implementation Activities
| 33.33% | Partially | 0.995% | SI.1 Software Implementation Initiation | 0 | 0 | 2 | 0
| 33.33% | Partially | 3.483% | SI.2 Software Requirements Analysis | 0 | 0 | 7 | 0
| 33.33% | Partially | 3.98% | SI.3 Software Architectural and Detailed Design | 0 | 0 | 8 | 0
| 33.33% | Partially | 3.483% | SI.4 Software Construction | 0 | 0 | 7 | 0
| 33.33% | Partially | 5.473% | SI.5 Software Integration and Tests | 0 | 0 | 11 | 0
| 33.33% | Partially | 2.985% | SI.6 Product Delivery | 0 | 0 | 6 | 0
Process Average | 33.33% |  |  |  | 0 | 0 | 41 | 0
Total Non-executed Tasks |  |  | 50%
Process Total Average | 33%

## PM Table
ISO 29110 Basic Profil | [5 empty] | My little organization
Project Management Activities | ID | Task List | Input Products | Output Products | Roles | Is implemented | Input Products | Output Products | Roles | Comments & Observations
PM.1 Project Planning | PM.1.1 | Review the Statement of Work | Statement of Work | Statement of Work [reviewed] | PM TL | Partially
| PM.1.2 | Define with the Customer the Delivery Instructions of each one of the Deliverables specified in the Statement of Work. | Statement of Work [reviewed] | Project Plan - Delivery Instructions | PM CUS | Partially
| PM.1.3 | Identify the specific Tasks to be performed in order to produce the Deliverables and their Software Components identified in the Statement of Work. Include Tasks in the SI process along with verification, validation and reviews with Customer and Work Team Tasks to assure the quality of work products. Identify the Tasks to perform the Delivery Instructions. Document the Tasks. | Statement of Work [reviewed] | Project Plan - Tasks | PM TL | Partially
| PM.1.4 | Establish the Estimated Duration to perform each task. | Project Plan - Tasks | Project Plan - Estimated Duration | PM TL | Partially
| PM.1.5 | Identify and document the Resources: human, material, equipment and tools, standards, including the required training of the Work Team to perform the project. Include in the schedule the dates when Resources and training will be needed. | Statement of Work | Project Plan - Resources | PM TL | Partially
| PM.1.6 | Establish the Composition of Work Team assigning roles and responsibilities according to the Resources. | Project Plan - Resources | Project Plan - Composition of Work Team | PM TL | Partially
| PM.1.7 | Assign estimated start and completion dates to each one of the Tasks in order to create the Schedule of the Project Tasks taking into account the assigned Resources, sequence and dependency of the Tasks. | Project Plan - Tasks - Estimated Duration - Composition of Work Team | Project Plan - Schedule of the Project Tasks | PM TL | Partially
| PM.1.8 | Calculate and document the project Estimated Effort and Cost. | Project Plan - Schedule of the Project Tasks - Resources | Project Plan - Estimated Effort and Cost | PM | Partially
| PM.1.9 | Identify and document the risks which may affect the project. | All elements previously defined | Project Tasks | PM TL | Partially
| PM.1.10 | Document the Version Control Strategy in the Project Plan. |  | Project Plan - Version Control Strategy | PM TL | Partially
| PM.1.11 | Generate the Project Plan integrating the elements previously identified and documented. | All elements previously defined | Project Plan - Tasks - Estimated Duration - Resources - Composition of Work Team - Schedule of the Project Task - Estimated Effort and Cost - Identification of Project Risks - Version Control Strategy - Delivery Instructions | PM | Partially
| PM.1.12 | Include Product Description, Scope, Objectives and Deliverables in the Project Plan. | Statement of Work - Product Description - Scope - Objectives - Deliverables | Project Plan - Product Description - Scope - Objectives - Deliverables | PM TL | Partially
| PM.1.13 | Verify and obtain approval of the Project Plan. Verify that all Project Plan elements are viable and consistent. The results found are documented in a Verification Results and corrections are made until the document is approved by PM. | Project Plan | Verification Results Project Plan [verified] | PM TL | Partially
| PM.1.14 | Review and accept the Project Plan. Customer reviews and accepts the Project Plan, making sure that the Project Plan elements match with the Statement of Work. | Project Plan [verified] | Meeting Record Project Plan [accepted] | PM CUS | Partially
| PM.1.15 | Establish the Project Repository using the Version Control Strategy. | Version Control Strategy | Project Repository | PM TL | Partially
PM.2 Project Plan Execution | PM.2.1 | Monitor the Project Plan execution and record actual data in Progress Status Record. | Project Plan | Progress Status Record | PM TL WT | Partially
| PM.2.2 | Analyse and evaluate the Change Request for cost, schedule and technical impact. The Change Request can be initiated externally by the Customer or internally by the Work Team. Update the Project Plan, if the accepted change does not affect agreements with Customer. Change Request, which affects those agreements, needs to be negotiated by both parties (see PM.2.4). | Change Request [initiated] Project Plan | Change Request [evaluated] Project Plan [updated] | PM TL | Partially
| PM.2.3 | Conduct revision meetings with the Work Team, identify problems, review risk status, record agreements and track them to closure. | Project Plan Progress Status Record Correction Register Meeting Record | Meeting Record [updated] | PM TL WT | Partially
| PM.2.4 | Conduct revision meetings with the Customer, record agreements and track them to closure. Change Request initiated by Customer or initiated by Work Team, which affects the Customer, needs to be negotiated to reach acceptance of both parties. If necessary, update the Project Plan according to new agreement with Customer. | Project Plan Progress Status Record Change Request [evaluated] Meeting Record | Meeting Record [updated] Change Request [accepted] Project Plan [updated] | PM CUS TL WT | Partially
| PM.2.5 | Perform backup according to the Version Control Strategy. | Version Control Strategy | Project Repository Backup | PM | Partially
| PM.2.6 | Perform Project Repository recovery using the Project Repository Backup, if necessary. | Project Repository Backup | Project Repository [recovered] | PM | Partially
PM.3 Project Assessment and Control | PM.3.1 | Evaluate project progress with respect to the Project Plan, comparing: - actual Tasks against planned Tasks - actual results against established project Objectives - actual resource allocation against planned Resources - actual cost against budget estimates - actual time against planned schedule - actual risk against previously identified | Project Plan Progress Status Record | Progress Status Record [evaluated] | PM TL WT | Partially
| PM.3.2 | Establish actions to correct deviations or problems and identified risks concerning the accomplishment of the plan, as needed, document them in Correction Register and track them to closure. | Progress Status Record [evaluated] | Correction Register | PM TL WT | Partially
| PM.3.3 | Identify changes to requirements and/or Project Plan to address major deviations, potential risks or problems concerning the accomplishment of the plan, document them in Change Request and track them to closure. | Progress Status Record [evaluated] | Change Request [initiated] | PM TL WT | Partially
PM.4 Project Closure | PM.4.1 | Formalize the completion of the project according to the Delivery Instructions established in the Project Plan, providing acceptance support and getting the Acceptance Record signed. | Project Plan - Delivery Instructions Software Configuration [delivered] | Acceptance Record Software Configuration [accepted] | PM CUS | Partially
| PM.4.2 | Update Project Repository. | Software Configuration [accepted] Project Repository | Project Repository [updated] | PM | Partially

## SI Table
ISO 29110 Basic Profil | [5 empty] | My little organization
Software Implementation Activities | ID | Task List | Input Products | Output Products | Roles | Is implemented | Input Products | Output Products | Roles | Comments & Observations
SI.1 Software Implementation Initiation | SI.1.1 | Revision of the current Project Plan with the Work Team members in order to achieve a common understanding and get their engagement with the project. | Project Plan | Project Plan[reviewed] | PM TL WT | Partially
| SI.1.2 | Set or update the implementation environment. | Project Plan [reviewed] |  | TL WT | Partially
SI.2 Software Requirements Analysis | SI.2.1 | Assign Tasks to the Work Team members in accordance with their role, based on the current Project Plan. | Project Plan [reviewed] - Tasks |  | TL WT | Partially
| SI.2.2 | Document or update the Requirements Specification. Identify and consult information sources (Customer, users, previous systems, documents, etc.) in order to get new requirements. Analyze the identified requirements to determinate the Scope and feasibility. Generate or update the Requirements Specification. | Project Plan - Product Description | Requirements Specification | AN CUS | Partially
| SI.2.3 | Verify and obtain approval of the Requirements Specification. Verify the correctness and testability of the Requirements Specification and its consistency with the Product Description. Additionally, review that requirements are complete, unambiguous and not contradictory. The results found are documented in a Verification Results and corrections are made until the document is approved by AN. If significant changes were needed, initiate a Change Request. | Requirements Specification Project Plan - Product Description | Verification Results Requirements Specification [verified] Change Request [initiated] | AN TL | Partially
| SI.2.4 | Validate and obtain approval of the Requirements Specification. Validate that Requirements Specification satisfies needs and agreed upon expectations, including the user interface usability. The results found are documented in a Validation Results and corrections are made until the document is approved by the CUS. | Requirements Specification [verified] | Validation Results Requirements Specification [validated] | CUS AN | Partially
| SI.2.5 | Document the preliminary version of the *Software User Documentation or update the present manual, if appropriate. *(Optional) | Requirements Specification [validated] | *Software User Documentation [preliminary] | AN | Partially
| SI.2.6 | Verify and obtain approval of the *Software User Documentation, if appropriate. Verify consistency of the *Software User Documentation with the Requirements Specification. The results found are documented in a Verification Results and corrections are made until the document is approved by AN. If significant changes were needed, initiate a Change Request. *(Optional) | *Software User Documentation [preliminary] Requirements Specification | Verification Results *Software User Documentation [preliminary, verified] Change Request [initiated] | AN | Partially
| SI.2.7 | Incorporate the Requirements Specification, and *Software User Documentation to the Software Configuration in the baseline. *(Optional) | Requirements Specification [validated] *Software User Documentation [preliminary, verified] | Software Configuration - Requirements Specification [validated, baselined] - *Software User Documentation [preliminary, verified, baselined] | TL | Partially
SI.3 Software Architectural and Detailed Design | SI.3.1 | Assign Tasks to the Work Team members related to their role according to the current Project Plan. | Project Plan - Tasks |  | TL AN DES | Partially
| SI.3.2 | Understand Requirements Specification. | Requirements Specification [validated, baselined] |  | AN DES | Partially
| SI.3.3 | Document or update the Software Design. Analyze the Requirements Specification to generate the architectural design, its arrangement in subsystems and Software Components defining the internal and external interfaces. Describe in detail, the appearance and the behaviour of the interface, based on the Requirements Specification in a way that Resources for its implementation can be foreseen. Provide the detail of Software Components and their interfaces to allow the construction in an evident way. Generate or update the Traceability Record. | Requirements Specification [validated, baselined] | Software Design Traceability Record | AN DES | Partially
| SI.3.4 | Verify and obtain approval of the Software Design. Verify correctness of Software Design documentation, its feasibility and consistency with their Requirement Specification. Verify that the Traceability Record contains the adequate relationships between requirements and the Software Design elements. The results found are documented in a Verification Results and corrections are made until the document is approved by DES. If significant changes were needed, initiate a Change Request. | Software Design Traceability Record Requirements Specification [validated, baselined] | Verification Results Software Design [verified] Traceability Record [verified] Change Request [initiated] | AN DES | Partially
| SI.3.5 | Establish or update Test Cases and Test Procedures for integration testing based on Requirements Specification and Software Design. Customer provides testing data, if needed. | Requirements Specification [validated, baselined] Software Design [verified, baselined] | Test Cases and Test Procedures | DES | Partially
| SI.3.6 | Verify and obtain approval of the Test Cases and Test Procedures. Verify consistency among Requirements Specification, Software Design and Test Cases and Test Procedures. The results found are documented in a Verification Results and corrections are made until the document is approved by AN. | Test Cases and Test Procedures Requirements Specification [validated, baselined] Software Design [verified, baselined] | Verification Results Test Cases and Test Procedures [verified] | DES AN | Partially
| SI.3.7 | Update the Traceability Record incorporating the Test Cases and Test Procedures. | Test Cases and Test Procedures [verified] Traceability Record [updated] | Traceability Record [updated] | DES | Partially
| SI.3.8 | Incorporate the Software Design, and Traceability Record to the Software Configuration as part of the baseline. Incorporate the Test Cases, and Test Procedures to the Project Repository. | Software Design [verified] Test Cases and Test Procedures [verified] Traceability Record [verified] | Software Configuration - Software Design [verified, baselined] - Test Cases and Test Procedures [verified] - Traceability Record [verified, baselined] | TL | Partially
SI.4 Software Construction | SI.4.1 | Assign Tasks to the Work Team members related to their role, according to the current Project Plan. | Project Plan - Tasks |  | TL | Partially
| SI.4.2 | Understand Software Design. | Software Design [verified, baselined] |  | PR | Partially
| SI.4.3 | Construct or update Software Components based on the detailed part of the Software Design. | Software Design [verified, baselined], Traceability Record [verified, baselined] | Software Components | PR | Partially
| SI.4.4 | Design or update unit test cases and apply them to verify that the Software Components implements the detailed part of the Software Design. | Software Components | Software Components [unit tested] | PR | Partially
| SI.4.5 | Correct the defects found until successful unit test (reaching exit criteria) is achieved. | Software Components [unit tested] | Software Components [corrected] | PR | Partially
| SI.4.6 | Update the Traceability Record incorporating Software Components constructed or modified. | Software Components [corrected] Traceability Record [verified, baselined] | Traceability Record [updated] | PR | Partially
| SI.4.7 | Incorporate Software Components and Traceability Record to the Software Configuration as part of the baseline. | Software Components [corrected] Traceability Record [updated] | Software Configuration - Software Components [corrected, baselined] - Traceability Record [updated baselined] | TL | Partially
SI.5 Software Integration and Tests | SI.5.1 | Assign Tasks to the work team members related to their role, according to the current Project Plan. | Project Plan - Tasks |  | TL | Partially
| SI.5.2 | Understand Test Cases and Test Procedures. Set or update the testing environment. | Test Cases and Test Procedures [verified] |  | PR | Partially
| SI.5.3 | Integrates the Software using Software Components and updates Test Cases and Test Procedures for integration testing, as needed. | Software Components [corrected, baselined] Test Cases and Test Procedures [verified] Traceability Record [updated, baselined] | Software Test Cases and Test Procedures | PR | Partially
| SI.5.4 | Perform Software tests using Test Cases and Test Procedures for integration and document results in Test Report. | Software Test Cases and Test Procedures | Software [tested] Test Report | PR CUS | Partially
| SI.5.5 | Correct the defects found and perform regression test until exit criteria is achieved. | Software [tested] Test Report Test Cases and Test Procedures Traceability Record [updated, baselined] | Software [corrected] Test Report [defects eliminated] | PR | Partially
| SI.5.6 | Updates the Traceability Record, if appropriate. | Software [corrected] Traceability Record [updated, baselined] | Traceability Record [updated] | PR | Partially
| SI.5.7 | Document the *Product Operation Guide or update the current guide, if appropriate. *(Optional) | Software [tested] | *Product Operation Guide | PR | Partially
| SI.5.8 | Verify and obtain approval of the *Product Operation Guide, if appropriate (see SI.5.7) Verify consistency of the Product Operation Guide with the Software. The results found are documented in a Verification Results and corrections are made until the document is approved by DES. *(Optional) | *Product Operation Guide Software [tested] | Verification Results *Product Operation Guide [verified] | PR CUS | Partially
| SI.5.9 | Document the *Software User Documentation or update the current one, if appropriate. *(Optional) | Software [tested] *Software User Documentation [preliminary] | *Software User Documentation | AN | Partially
| SI.5.10 | Verify and obtain approval of the *Software User Documentation, if appropriate (see SI.5.9) Verify consistency of the Software User Documentation with the Software. The results found are documented in a Verification Results and corrections are made until the document is approved by CUS. *(Optional) | *Software User Documentation Software [tested] | Verification Results *Software User Documentation [verified] | AN CUS | Partially
| SI.5.11 | Incorporate the Test Cases and Test Procedures, Software, Traceability Record, Test Report, *Product Operation Guide and *Software User Documentation to the Software Configuration as part of the baseline. *(Optional) | Test Cases and Test Procedures Software [tested] Test Report Traceability Record [updated] *Product Operation Guide [verified] *Software User Documentation [verified] | Software Configuration - Test Cases and Test Procedures [baselined] - Software [tested, baselined] - Traceability Record [updated, baselined] - Test Report [baselined] - *Product Operation Guide [verified, baselined] - *Software User Documentation [verified, baselined] | TL | Partially
SI.6 Product Delivery | SI.6.1 | Assign Tasks to the work team members related to their role, according to the current Project Plan. | Project Plan - Tasks |  | TL WT | Partially
| SI.6.2 | Understand Software Configuration. | Software Configuration |  | DES | Partially
| SI.6.3 | Document the Maintenance Documentation or update the current one. | Software Configuration | Maintenance Documentation | DES | Partially
| SI.6.4 | Verify and obtain approval of the Maintenance Documentation. Verify consistency of Maintenance Documentation with Software Configuration. The results found are documented in a Verification Results and corrections are made until the document is approved by TL. | Maintenance Documentation Software Configuration | Verification Results Maintenance Documentation [verified] | DES | Partially
| SI.6.5 | Incorporate the Maintenance Documentation as baseline for the Software Configuration. | Software Configuration Maintenance Documentation [verified] | Software Configuration - Maintenance Documentation [verified, baselined] | TL | Partially
| SI.6.6 | Perform delivery according to Delivery Instructions. | Project Plan - Delivery Instructions Software Configuration | Software Configuration [delivered] | TL | Partially

## Role
Norme ISO 29110-5 |  |  | My little organization
Role | Abbreviation | Competency | Role | Abbreviation | Competency | Comments & Observations
Analyst | AN | Knowledge and experience eliciting, specifying and analyzing the requirements. Knowledge in designing user interfaces and ergonomic criteria. Knowledge of the revision techniques. Knowledge of the editing techniques. Experience on the software development and maintenance. | Analyst | AN
Customer | CUS | Knowledge of the Customer processes and ability to explain the Customer requirements. The Customer (representative) must have the authority to approve the requirements and their changes. The Customer includes user representatives in order to ensure that the operational environment is addressed. Knowledge and experience in the application domain. | Customer | CUS
Designer | DES | Knowledge and experience in the Software Components and architecture design. Knowledge of the revision techniques. Knowledge and experience in the planning and performance of integration tests. Knowledge of the editing techniques. Experience on the software development and maintenance. | Designer | DES
Programmer | PR | Knowledge and/or experience in programming, integration and unit tests. Knowledge of the revision techniques. Knowledge of the editing techniques. Experience on the software development and maintenance. | Programmer | PR
Project Manager | PM | Leadership capability with experience making decisions, planning, personnel management, delegation and supervision, finances and software development. | Project Manager | PM
Technical Leader | TL | Knowledge and experience in the software process domain. | Chef d'équipe | TL
Work Team | WT | Knowledge and experience according to their roles on the project. | Work Team | WT

## Extra
Implemented
Fully |  | Full | Large | Partial | No
Largely |  | Fully | Largely | Partially | No | Partially | 0.325 | Fully | 1 | No | 0 | Largely | 0.675 | Fully | 1
Partially | value | 100% | 67.5% | 32.5% | 0% | Fully | 1 | Largely | 0.675 | Partially | 0.325 | Largely | 0.675 | Largely | 0.675
No | Trigger | 85% | 50% | 15% | 0% | Fully | 1 | Fully | 1 | Partially | 0.325 | No | 0 | Partially | 0.325
[10 empty] | Largely | 0.675 | No | 0 | Partially | 0.325
[10 empty] | Largely | 0.675 | Partially | 0.325 | Partially | 0.325
Profile | [11 empty] | Largely | 0.675 | Partially | 0.325
Entry
Basic
[6 empty] | Largely | 0.775 | Fully | 0.89167 | Partially | 0.4 | Partially | 0.39167 | Partially | 0.49583
Organization Name
My little organization
- P,F,F -> overall L
- F,L,F -> overall F
- N,P,P,L,L -> overall P
- L,L,N,N,P,L -> overall P
- F,L,P,P,P,P -> overall P or L (based on assessor's judgment)